## Slide 1: Tour Booking Management System
Hengpan Han, Wen Liang, Arnold Aristotle Tayag
MSE800 – Professional Software Engineering
Yoobee College of Creative Innovation

## Slide 2: Introduction
As the tourism industry grows rapidly, an online tour booking system has become essential for tourists and operators. To address this, we are developing a Tour Booking Management System. This system will help users quickly search and book tours while providing operators with tools to manage their offerings. The frontend will use HTML, CSS, and JavaScript, while Node.js and Python will handle backend logic. Agile methodology will be used and a duration of one–week sprint for development is adopted to allow flexibility in meeting user requirements.
The goal of this project is to create a user-friendly platform for tourists to find tour information, book, pay, cancel reservations, and leave reviews. Operators and administrators will have tools to manage tours, user accounts, generate reports, and monitor system performance to ensure efficiency.
The project focuses on New Zealand tours, including browsing information, online booking, reviews, and monitoring. The development will be divided into three releases. A minimum viable product (MVP) will be available in the first release and gradually adding features at each stage.

## Slide 3: Project Overview
Key Features:
Tour Browsing: View detailed information (description, price, schedule, ratings).
Manage Online Booking: Secure booking, email confirmations, real-time status updates.
Payment Processing: Integration with payment gateways to facilitate secure online transactions.
User Registration and Profiles: Users can create accounts to manage bookings, save favorite tours, and receive personalized recommendations
Tour Review: Users can leave reviews and rate their experiences, helping future customers make informed decisions.
Admin Interface: Manage user accounts, generate reports, and monitor system performance.
System Monitoring & Reporting: Centralized performance and error log tracking.
Customer Support: Email support for inquiries.
System Integration: API for third-party integrations.
Benefits:
User-Friendly Interface: Intuitive design ensures users can easily navigate the system and find suitable tours
Streamlined Operations: Helps tour operators manage bookings and customer interactions efficiently
Cultural Sensitivity: By including tours that focus on local Māori culture and history, the system can respect and promote indigenous perspectives
Increased Visibility: Operators can showcase their tours to a wider audience, increasing bookings and revenue

## Slide 4: Project Plan
System Environment:
Backend: Node.js + Python
Frontend: HTML, CSS, JavaScript (React/Vue)
Database: SQLite
Hosting: Local server or cloud-based
Tools: Git for version control, Jira for project management
GitHub repository: https://github.com/aamtayag/mse800-assessment2.git
Development Approach:
Agile methodology (Scrum + XP)
1-week sprint
Fibonacci estimation
Stakeholders:
Product Owner / Business Users (Tourists/Customers/Tour Operators/Tour Owners) / Stakeholders / Sponsor: Provides requirements and feedback on the product's functionality.
Agile Facilitator: Oversees project progress, facilitates meetings, and ensures agile practices are followed.
Project Team: Responsible for designing, developing, and testing the system.

## Slide 5: Team Structure
Architect
Team Member: Arnold Aristotle Tayag
Responsible for the overall design of the system architecture, providing recommendations on the technical framework, structure and scalability of the project. The architect will take into account the requirements of system performance, scalability, and disaster recovery capability in the design to ensure that the technical implementation meets the business requirements.
Responsibility:
Develop and maintain the technical architecture and core design of the system
Guide technology selection and choose the right technology stack and tools for the project
Ensure the system has good scalability and efficient data processing capabilities
Collaborate with front and back-end teams to ensure proper implementation of architectural design
Frontend Developer
Team Member: Wen Liang
Responsible for the design and implementation of the user interface to ensure a smooth and intuitive user interaction experience in the system. They present the system functionality to the user in the best possible way according to the designer's visual requirements.
Responsibility:
Implement user interface design and interaction features to ensure compatibility on various devices
Collaborate with the back-end team to integrate APIs and ensure seamless interaction of data with the interface
Optimize front-end performance to improve system loading speed and response time
Focus on user experience details to optimise interface elements and interaction logic

## Slide 6: Team Structure
Backend Developer
Team Member: Hengpan He
Responsible for the implementation of the system's data processing and business logic, creating and maintaining API interfaces, which are the core support for the normal operation of system functions.
Responsibility:
Implement core business logic and handle complex data operations and processes
Design and implement system database and API interfaces to ensure smooth data interaction between front and back end
Configure system security to protect user data and prevent security breaches
Ensure the stability of the back-end system through unit testing and integration testing.
Project Manager
Team Member: Arnold Aristotle Tayag
Key coordinator and bridge of communication for project time planning, resource management and schedule control to ensure all teams work together efficiently.
Responsibility:
Manage project schedules to ensure phases are completed on time
Maintain open communication to ensure unobstructed flow of information between the client, development team and test team
Identify and manage project risks and develop prevention strategies
Organize regular project status meetings to support the team and resolve issues

## Slide 7: Project Kick-off Meeting
Meeting Objectives
Define the main functions of the system and the operating privileges of key user roles
Establish communication process and feedback mechanism to ensure timely problem solving during the development process
Identify project risks, analyze potential challenges and discuss initial response strategies.
Participants:
Client representative: Arnold Aristotle Tayag
Development team Representative: Wen Lian
Project Manager: Hengpan He
Outcomes:
Confirm the process of publishing basic information (e.g., name, description, price, etc.) about a tour product and the authority to modify it
Discuss the key steps in the booking process, including the process design for booking confirmation and cancellation
Clarify the notification mechanism for users and administrators to ensure transparency and real-time system operation.

## Slide 8: Project Kick-off Meeting
Outcomes:
Confirm the process of publishing basic information (e.g., name, description, price, etc.) about a tour product and the authority to modify it
Discuss the key steps in the booking process, including the process design for booking confirmation and cancellation
Clarify the notification mechanism for users and administrators to ensure transparency and real-time system operation
Discuss how to achieve efficient communication and ensure two-way feedback between the client team and the development team. Specifically includes:
  Weekly project update meetings to report on the week's progress and the work plan for the following week
  An assessment of the time point to the next milestone
  Task tracking and issue management using the project management tool Jira

## Slide 9: Project Kick-off Meeting
Project risks identification:
Identify technical or business challenges that may be encountered in the project, conduct risk analyses and initially discuss response strategies. Key considerations include:
User booking cancellation timeliness issues and system responsiveness during peak periods
System stability, including Service Level Agreement (SLA) related elements
Horizontal expansion capability of the system and disaster recovery requirements
Objectives and requirements of the system's core data storage and backup strategy

## Slide 10: Scope of Work
The system focuses on providing tour booking services exclusively for tours within New Zealand. It will cover the following key features:
Tour Browsing: Displays detailed information such as tour descriptions, prices, itineraries, and ratings.
Online Booking: Supports email confirmation, payment processing, and tracking of booking statuses.
Tour Review: Allows users to provide feedback and ratings after the tour.
User Management: Enables administrators to manage user accounts and permissions.
System Integration: Offers APIs for integrating with third-party payment services and tour information providers
Out of Scope
The following items are beyond the scope of this project:
Offline travel arrangements or services outside of New Zealand.
Travel insurance management: The system will not handle or process insurance requests or claims.
Multi-currency support: The platform will only process payments in New Zealand dollars (NZD) without exchange rate calculations.

## Slide 11: System Design
System Architecture
Frontend Technologies: The frontend will be developed using HTML, CSS, and JavaScript, ensuring a responsive and user-friendly interface for tourists and administrators.
Backend Technologies: The backend logic will be handled using a combination of Python and Node.js to efficiently manage business logic, API calls, and data processing.
Database: The system will use SQLite as the primary database to store data such as tour details, user information, bookings, and feedback
Module Breakdown
Tour Browsing Module: Loads available tours from the database and displays relevant information to the users based on their preferences.
Online Booking Module: Processes bookings and payments, updates booking status, and handles email confirmations.
Admin Interface: Provides system administrators with the ability to manage users, process booking requests, and generate reports.
Tour Review Module: Collects and displays feedback from users, including ratings and comments.
System Integration Module: Integrates with third-party services through APIs, such as payment gateways

## Slide 12: System Design
System Interfaces
Tour Listing Page: Displays all available tours and allows users to filter based on preferences like destination, date, and tour type.
User/Admin Login Page: Provides separate login interfaces for tourists and administrators.
Booking Page: Facilitates the booking process by collecting traveler details, confirming availability, and processing payments.
Data Flow and Communication
Frontend and Backend Communication: The frontend will communicate with the backend using REST APIs to ensure smooth data exchange. Node.js will handle API requests, while Python will manage the business logic and data processing.
Database Operations: SQLite will store all necessary data, including user accounts, tours, bookings, and reviews. The backend will manage data queries and ensure synchronization between modules.
Scalability Considerations: Although SQLite is a lightweight database suitable for the initial development phase, the system architecture allows for future migration to more robust databases (e.g., MySQL or PostgreSQL) if needed.

## Slide 13: Project Backlog Prioritization
User Story # | Functionality | User Story | Acceptance Criteria | Prioritization
1 | For Tourists, Customers | As a tourist, I want to browse available tours, so that I can find options that interest me | Users can filter tours by category, location, and price | Release 1
2 | For Tourists, Customers | As a tourist, I want to view detailed information about each tour, so that I can make informed decisions | Each tour page includes a description, itinerary, duration, price, and reviews | Release 1
3 | For Tourists, Customers | As a tourist, I want to book a tour online, so that I can secure my spot easily | Users can select dates, number of participants, and complete payment through a secure gateway | Release 1
4 | For Tourists, Customers | As a tourist, I want to receive confirmation emails after booking, so that I have all the details at hand | A confirmation email is sent immediately after booking, containing all relevant details | Release 1

## Slide 14: Project Backlog Prioritization
5 | For Tourists, Customers | As a tourist, I want to be able to cancel or modify my booking, so that I can manage my plans flexibly | Users can cancel or modify bookings within a specified time frame, with a clear refund policy | Release 1
6 | For Tourists, Customers | As a tourist, I want to leave reviews for tours I’ve taken, so that I can share my experiences with others | Users can rate tours and provide written feedback after the tour is completed | Release 2
7 | For Tourists, Customers | As a user, I want to log in and set my language preference (e.g., Māori) | Users can set preferred language to any language supported by the system | Release 1
8 | For Tour Operators, Administrators | As a tour operator, I want to create and manage tour listings, so that I can keep my offerings up to date | Operators can add, edit, or delete tours and manage details like pricing and availability | Release 2

## Slide 15: Project Backlog Prioritization
9 | For Tour Operators, Administrators | As a tour operator, I want to view booking reports and analytics, so that I can assess the performance of my tours | Operators can access dashboards showing sales, cancellations, and customer feedback | Release 2
10 | For Tour Operators, Administrators | As a tour operator, I want to manage customer inquiries, so that I can provide timely responses | Operators have a messaging system to communicate with customers regarding inquiries or concerns | Release 2
11 | For Tour Operators, Administrators | As a tour operator, I want to set seasonal pricing and promotions, so that I can attract more customers | Operators can schedule discounts and special offers that apply to specific dates or tours | Release 2
12 | For Tour Operators, Administrators | As a tour operator, I want to manage payment processing, so that I can receive payments securely | The system integrates with payment gateways, allowing for secure transactions and providing operators with transaction reports | Release 1
13 | For Admins | As an admin, I want to manage user accounts, so that I can maintain the integrity of the platform | Admins can create, edit, and deactivate user accounts for both customers and operators | Release 1

## Slide 16: Project Backlog Prioritization
14 | For Admins | As an admin, I want to monitor system performance and error logs, so that I can ensure the system runs smoothly | Admins have access to performance metrics and can view logs for troubleshooting | Release 2
15 | For Admins | As an admin, I want to enforce policies and regulations for tour operators, so that the platform maintains quality standards | Admins can set guidelines for tour operators and review compliance | Release 3
16 | For Admins | As an admin, I want to generate reports on user activity and bookings, so that I can analyze system usage and revenue | Admins can generate customizable reports on various metrics | Release 2
17 | For Developers | As a developer, I want to ensure the system is responsive, so that users can book tours on any device | The booking platform functions seamlessly on mobile, tablet, and desktop | Release 1
18 | For Developers | As a developer, I want to implement secure payment processing, so that user financial information is protected | The payment system complies with industry standards for security (e.g., PCI DSS) | Release 1
19 | For Developers | As a developer, I want to create an API for third-party integrations, so that the system can connect with other applications | The API provides endpoints for tour listings, bookings, and user management | Release 3

## Slide 17: Release Planning
Release Plan:
Release 1:
Tour browsing
description about the tour
Price
schedule (place, time, activities)
Online booking
send booking email confirmation
booking cancellation
online secure payment
booking status: booked, paid, cancelled, modify
Admin Interface
manage user accounts
user types: customer, system users (user, admin)
activities: customer + user creation, change privilege
Customer Support
send email for clarifications

## Slide 18: Release Planning
Release Plan:
Release 2:
Tour browsing
show computed average rating
tour management
Tour review
1 rating from 1 to 5
customer comments/recommendations
Admin Interface
report generation
System Monitoring & Reporting
system performance
monitor error logs
booking report and analytics
Release 3:
System integration
API for third-party integrations

## Slide 19: Sprint Planning
User Story # | Estimation (Fibonacci) | Sprint Number
1 | 2 | 1
2 | 2 | 1
3 | 5 | 1
4 | 5 | 2
5 | 5 | 2
7 | 5 | 2
12 | 4 | 3
13 | 5 | 3
17 | 13 | 4
18 | 4 | 4
Sprint Plan for Release 1

## Slide 20: Sprint Planning
User Story # | Estimation (Fibonacci) | Sprint Number
6 | 3 | 1
8 | 5 | 1
9 | 8 | 2
10 | 5 | 2
11 | 5 | 3
14 | 8 | 3
16 | 8 | 4
Sprint Plan for Release 2

## Slide 21: Sprint Planning
User Story # | Estimation (Fibonacci) | Sprint Number
15 | 8 | 1
19 | 13 | 2
Sprint Plan for Release 3

## Slide 22: Costing / Budget
Assumptions:
1. Sample budget outline (baseline only) for a Tour Booking Management System, broken down into Development, Infrastructure, and Operational expenses
2. Budget allocated is based on a mid–sized tour agency
3. Actual cost will vary based on system complexity, user volume, and additional features, such as analytics or advanced reporting features
1. Development Costs
a. Planning & Design
Market Research & Feasibility Study: $1,500 - $3,000
Requirement Gathering and Documentation: $1,500 - $3,000
System Architecture Design: $1,500 - $3,000
b. Software Development
Frontend Development (HTML, CSS, Javascript (React/Angular/Vue)): $5,000 - $10,000
Backend Development (Node.js/Django): $10,000 - $20,000
Database Setup (SQLite): $1,000 - $2,000
System Integration: $5,000 - $10,000
Payment Gateway Integration: $2,000 - $5,000
c. Testing & Quality Assurance
Automated & Manual Testing: $3,000 - $6,000
User Acceptance Testing (UAT): $1,000 - $3,000
2. Infrastructure & Licensing Costs
a. Hosting & Server Costs
Cloud Hosting (AWS, Azure, or Google Cloud): $100 - $500/month
Domain Name Registration: $10 - $30/year
SSL Certificate: $50 - $200/year
b. Software Licensing & Subscriptions
Booking & CRM Software Integration: $500 - $2,000/year
Payment Gateway Fees (Stripe, PayPal, etc.): 2.9% + $0.30 per transaction
Analytics Tools (Google Analytics): $10 - $100/month
3. Operational Costs
a. Content Creation & Marketing
Graphic Design: $1,000 - $2,500
SEO & Marketing: $300 - $1,000/month
b. Ongoing Maintenance & Updates
System Maintenance & Bug Fixes: $1,000 - $2,500/month
Feature Updates & Enhancements: $2,000 - $4,500/quarter
c. Staff Training & Support
Training Sessions for Admin & Staff: $500 - $1,500
Documentation Creation: $500 - $1,500
Total Estimated Cost:
Initial Development & Setup Costs: $36,000 - $81,000
Ongoing Monthly Costs: $2,000 - $5,000
Total Yearly Operational Cost: $26,000 - $66,000

## Slide 23: Project Sign-Off
Project Title : Tour Booking Management System Project ID : Alpha-1xB.1257 Date : 31 October 2024 Project Manager : Wen Liang Client/Stakeholder : Arnold Aristotle Tayag
Project Overview
This project, i.e. Tour Booking Management System, is intended to streamline and automate the processes involved in booking tours, its management, tracking, and reporting. The system envisions to enhance user experience while also improving the efficiency in managing bookings and providing real-time management and administration for system users.
Deliverables Checklist
The following project deliverables have been completed, reviewed, and approved:
Deliverable Status Comments
Requirement Specification Completed _________
System Design Document Completed _________
Database Design Completed _________
Application Development Completed _________
System Testing Completed _________
User Acceptance Testing (UAT) Completed _________
Training & Documentation Completed _________
Go-Live/Deployment Completed _________
Acceptance Criteria
All project requirements, deliverables, and acceptance criteria have been reviewed and meet the standards agreed upon in the original project plan, including:
Functional and non-functional requirements
Performance and scalability requirements
Security and compliance requirements
Usability and user interface requirements
Sign-Off
By affixing your signature below, both parties agree that the project meets all user specifications and requirements and is considered officially complete. Any addendum, modifications, enhancements, or new functionalities added will be treated as new requirements and will be the subject of a new project proposal.
Role Name Signature Date
Project Manager Wen Liang _________ 31 October 2024
Client/Stakeholder Arnold Aristotle Tayag _________ 31 October 2024
Technical Lead Hengpan Han _________ 31 October 2024

## Slide 24: Thank You...