## Slide 1: Tour Booking Management System
Hengpan Han, Wen Liang, Arnold Aristotle Tayag
MSE800 (Professional Software Engineering)
Yoobee College of Creative Innovation

## Slide 2: Introduction
As the tourism industry grows rapidly, an online tour booking system has become essential for tourists and operators. To address this, we are developing a Tour Booking Management System. This system will help users quickly search and book tours while providing operators with tools to manage their offerings. The frontend will use HTML, CSS, and JavaScript, while Node.js and Python will handle backend logic. Agile methodology will be used and a duration of one–week sprint for development is adopted to allow flexibility in meeting user requirements.
The goal of this project is to create a user-friendly platform for tourists to find tour information, book, pay, cancel reservations, and leave reviews. Operators and administrators will have tools to manage tours, user accounts, generate reports, and monitor system performance to ensure efficiency.
The project focuses on New Zealand tours, including browsing information, online booking, reviews, and monitoring. The development will be divided into three releases. A minimum viable product (MVP) will be available in the first release and gradually adding features at each stage.

## Slide 3: Project Overview
Key Features:
Release 1:
  Tour Browsing: View detailed information (description, price, schedule, ratings)
  Manage Online Booking: Secure booking, email confirmations, real-time status updates
  Payment Processing: Integration with payment gateways to facilitate secure online transactions
  Admin Interface: Manage user accounts, generate reports, and monitor system performance
Release 2 & 3:
  Customer Support: Email support for inquiries
  Tour Review: Users can leave reviews and rate their experiences, helping future customers make informed decisions
  System Monitoring & Reporting: Centralized performance and error log tracking
  User Registration and Profiles: Users can create accounts to manage bookings, save favorite tours, and receive personalized recommendations
  System Integration: API for third-party integrations
Benefits:
  User-Friendly Interface: Intuitive design ensures users can easily navigate the system and find suitable tours
  Streamlined Operations: Helps tour operators manage bookings and customer interactions efficiently
  Cultural Sensitivity: By including tours that focus on local Māori culture and history, the system can respect and promote indigenous perspectives
  Increased Visibility: Operators can showcase their tours to a wider audience, increasing bookings and revenue

## Slide 4: Project Plan
Development Environment:
  Frontend: HTML, CSS, JavaScript (React/Vue)
  Backend: Node.js + Python
  Database: SQLite
  Hosting: Local server or cloud-based
  Tools: Git for version control, Jira for project management
  GitHub repository: https://github.com/aamtayag/mse800-assessment2.git
Development Approach:
  Agile methodology (Scrum + XP)
  1-week sprint
  Fibonacci estimation: 1, 2, 3, 5, 8, 13
Stakeholders:
  Product Owner / Business Users (Tourists/Customers/Tour Operators/Tour Owners) / Stakeholders / Sponsor – provides requirements and feedback on the product's functionality
  Agile Facilitator/Project Manager – oversees project progress, facilitates meetings, and ensures agile practices are followed
  Project Team – responsible for designing, developing, and testing the system

## Slide 5: Team Structure
Architect
Team Member: Arnold Aristotle Tayag
Responsibility:
  Responsible for the overall design of the system architecture
  Develop and maintain the technical architecture and core design of the system
  Guide technology selection and choose the right technology stack and tools for the project
  Ensure the system has good scalability and efficient data processing capabilities
  Collaborate with front and back-end teams to ensure proper implementation of architectural design
Frontend Developer
Team Member: Wen Liang
Responsibility:
  Responsible for the design and implementation of the user interface
  Implement user interface design and interaction features to ensure compatibility on various devices
  Collaborate with the back-end team to integrate APIs and ensure seamless interaction of data with the interface
  Optimize front-end performance to improve system loading speed and response time
  Focus on user experience details to optimise interface elements and interaction logic

## Slide 6: Team Structure
Backend Developer
Team Member: Hengpan He
Responsibility:
  Responsible for the implementation of the system's data processing and business logic
  Implement core business logic and handle complex data operations and processes
  Design and implement system database and API interfaces to ensure smooth data interaction between front and back end
  Configure system security to protect user data and prevent security breaches
  Ensure the stability of the back-end system through unit testing and integration testing.
Project Manager
Team Member: Arnold Aristotle Tayag
Responsibility:
  Key coordinator and bridge of communication for project time planning, resource management and schedule control
  Manage project schedules to ensure phases are completed on time
  Maintain open communication to ensure unobstructed flow of information between the client, development team and test team
  Identify and manage project risks and develop prevention strategies
  Organize regular project status meetings to support the team and resolve issues

## Slide 7: Project Kick-off Meeting
Meeting Objectives
  Define the main functions of the system and the operating privileges of key user roles
  Establish communication process and feedback mechanism to ensure timely problem solving during the development process
  Identify project risks, analyze potential challenges and discuss initial response strategies.
Key Participants:
  Client representative: Arnold Aristotle Tayag
  Development team Representative: Wen Lian
  Project Manager: Hengpan He
Meeting Outcomes:
  Confirm the process of publishing basic information (e.g., name, description, price, etc.) about a tour product and the authority to modify it
  Discuss the key steps in the booking process, including the process design for booking confirmation and cancellation
  Clarify the notification mechanism for users and administrators to ensure transparency and real-time system operation
  Discuss the key steps in the booking process, including the process design for booking confirmation and cancellation

## Slide 8: Project Kick-off Meeting
Meeting Outcomes:
  Confirm the process of publishing basic information (e.g., name, description, price, etc.) about a tour product and the authority to modify it
  Clarify the notification mechanism for users and administrators to ensure transparency and real-time system operation
  Discuss how to achieve efficient communication and ensure two-way feedback between the client team and the development team. Specifically includes:
    Weekly project update meetings to report on the week's progress and the work plan for the following week
    An assessment of the time point to the next milestone
    Task tracking and issue management using the project management tool Jira
Project risks identification:
  Identify technical or business challenges that may be encountered in the project, conduct risk analyses and initially discuss response strategies. Key considerations include:
    User booking cancellation timeliness issues and system responsiveness during peak periods
    System stability, including Service Level Agreement (SLA) related elements
    Horizontal expansion capability of the system and disaster recovery requirements
    Objectives and requirements of the system's core data storage and backup strategy

## Slide 9: Scope of Work
The system focuses on providing tour booking services exclusively for tours within New Zealand. It will cover the following key features:
  Tour Browsing: Displays detailed information such as tour descriptions, prices, itineraries, and ratings.
  Online Booking: Supports email confirmation, payment processing, and tracking of booking statuses.
  Tour Review: Allows users to provide feedback and ratings after the tour.
  User Management: Enables administrators to manage user accounts and permissions.
  System Integration: Offers APIs for integrating with third-party payment services and tour information providers
The following items are beyond the scope of this project:
  Offline travel arrangements or services outside of New Zealand
  Travel insurance management: The system will not handle or process insurance requests or claims
  Multi-currency support: The platform will only process payments in New Zealand dollars (NZD) without exchange rate calculations

## Slide 10: System Design
System Architecture:
  Frontend Technologies: The frontend will be developed using HTML, CSS, and JavaScript, ensuring a responsive and user-friendly interface for tourists and administrators
  Backend Technologies: The backend logic will be handled using a combination of Python and Node.js to efficiently manage business logic, API calls, and data processing
  Database: The system will use SQLite as the primary database to store data such as tour details, user information, bookings, and feedback
Module Breakdown:
  Tour Browsing Module: Loads available tours from the database and displays relevant information to the users based on their preferences
  Online Booking Module: Processes bookings and payments, updates booking status, and handles email confirmations
  Admin Interface: Provides system administrators with the ability to manage users, process booking requests, and generate reports
  Tour Review Module: Collects and displays feedback from users, including ratings and comments
  System Integration Module: Integrates with third-party services through APIs, such as payment gateways

## Slide 11: System Design
System Interfaces:
  Tour Listing Page: Displays all available tours and allows users to filter based on preferences like destination, date, and tour type
  User/Admin Login Page: Provides separate login interfaces for tourists and administrators
  Booking Page: Facilitates the booking process by collecting traveler details, confirming availability, and processing payments
Data Flow and Communication
  Frontend and Backend Communication: The frontend will communicate with the backend using REST APIs to ensure smooth data exchange. Node.js will handle API requests, while Python will manage the business logic and data processing
  Database Operations: SQLite will store all necessary data, including user accounts, tours, bookings, and reviews. The backend will manage data queries and ensure synchronization between modules
  Scalability Considerations: Although SQLite is a lightweight database suitable for the initial development phase, the system architecture allows for future migration to more robust databases (e.g., MySQL or PostgreSQL) if needed

## Slide 12: Project Backlog Prioritization
User Story # | Functionality | User Story | Acceptance Criteria | Prioritization
1 | For Tourists, Customers | As a tourist, I want to browse available tours, so that I can find options that interest me | Users can filter tours by category, location, and price | Release 1
2 | For Tourists, Customers | As a tourist, I want to view detailed information about each tour, so that I can make informed decisions | Each tour page includes a description, itinerary, duration, price, and reviews | Release 1
3 | For Tourists, Customers | As a tourist, I want to book a tour online, so that I can secure my spot easily | Users can select dates, number of participants, and complete payment through a secure gateway | Release 1
4 | For Tourists, Customers | As a tourist, I want to receive confirmation emails after booking, so that I have all the details at hand | A confirmation email is sent immediately after booking, containing all relevant details | Release 1

## Slide 13: Project Backlog Prioritization
User Story # | Functionality | User Story | Acceptance Criteria | Prioritization
5 | For Tourists, Customers | As a tourist, I want to be able to cancel or modify my booking, so that I can manage my plans flexibly | Users can cancel or modify bookings within a specified time frame, with a clear refund policy | Release 1
6 | For Tourists, Customers | As a tourist, I want to leave reviews for tours I’ve taken, so that I can share my experiences with others | Users can rate tours and provide written feedback after the tour is completed | Release 2
7 | For Tourists, Customers | As a user, I want to log in and set my language preference (e.g., Māori) | Users can set preferred language to any language supported by the system | Release 1
8 | For Tour Operators, Administrators | As a tour operator, I want to create and manage tour listings, so that I can keep my offerings up to date | Operators can add, edit, or delete tours and manage details like pricing and availability | Release 2

## Slide 14: Project Backlog Prioritization
9 | For Tour Operators, Administrators | As a tour operator, I want to view booking reports and analytics, so that I can assess the performance of my tours | Operators can access dashboards showing sales, cancellations, and customer feedback | Release 2
10 | For Tour Operators, Administrators | As a tour operator, I want to manage customer inquiries, so that I can provide timely responses | Operators have a messaging system to communicate with customers regarding inquiries or concerns | Release 2
11 | For Tour Operators, Administrators | As a tour operator, I want to set seasonal pricing and promotions, so that I can attract more customers | Operators can schedule discounts and special offers that apply to specific dates or tours | Release 2
12 | For Tour Operators, Administrators | As a tour operator, I want to manage payment processing, so that I can receive payments securely | The system integrates with payment gateways, allowing for secure transactions and providing operators with transaction reports | Release 1
13 | For Admins | As an admin, I want to manage user accounts, so that I can maintain the integrity of the platform | Admins can create, edit, and deactivate user accounts for both customers and operators | Release 1

## Slide 15: Project Backlog Prioritization
14 | For Admins | As an admin, I want to monitor system performance and error logs, so that I can ensure the system runs smoothly | Admins have access to performance metrics and can view logs for troubleshooting | Release 2
15 | For Admins | As an admin, I want to enforce policies and regulations for tour operators, so that the platform maintains quality standards | Admins can set guidelines for tour operators and review compliance | Release 3
16 | For Admins | As an admin, I want to generate reports on user activity and bookings, so that I can analyze system usage and revenue | Admins can generate customizable reports on various metrics | Release 2
17 | For Developers | As a developer, I want to ensure the system is responsive, so that users can book tours on any device | The booking platform functions seamlessly on mobile, tablet, and desktop | Release 1
18 | For Developers | As a developer, I want to implement secure payment processing, so that user financial information is protected | The payment system complies with industry standards for security (e.g., PCI DSS) | Release 1
19 | For Developers | As a developer, I want to create an API for third-party integrations, so that the system can connect with other applications | The API provides endpoints for tour listings, bookings, and user management | Release 3

## Slide 16: Release Planning
Release 1:
  Tour browsing
  Online booking
  Admin Interface
  Customer Support
Release 2:
  Tour browsing: show computed average rating, tour management
  Tour review: 1 rating from 1 to 5, customer comments/recommendations
  Admin Interface: report generation
  System Monitoring & Reporting: system performance, monitor error logs, booking report and analytics
Release 3:
  System integration
  API for third-party integrations

## Slide 17: Sprint Planning
Sprint Number | User Story # | Estimation (Fibonacci)
1 | 1 | 2
 | 2 | 2
 | 3 | 5
2 | 4 | 5
 | 5 | 5
 | 7 | 5
3 | 12 | 4
 | 13 | 5
4 | 17 | 13
 | 18 | 4
Sprint Plan for Release 1
Sprint Number | User Story # | Estimation (Fibonacci)
1 | 6 | 3
 | 8 | 5
2 | 9 | 8
 | 10 | 5
3 | 11 | 5
 | 14 | 8
4 | 16 | 8
Sprint Plan for Release 2
Sprint Number | User Story # | Estimation (Fibonacci)
1 | 15 | 8
2 | 19 | 13
Sprint Plan for Release 3

## Slide 18: Costing / Budget
Assumptions:
  Sample budget outline (baseline only) for a Tour Booking Management System, broken down into Development, Infrastructure, and Operational expenses
  Budget allocated is based on a mid–sized tour agency
  Actual cost will vary based on system complexity, user volume, and additional features, such as analytics or advanced reporting features
Development Costs:
  Planning & Design
  Software Development
  Testing & Quality Assurance
Infrastructure & Licensing Costs:
  Hosting & Server Costs
  Software Licensing & Subscriptions
Operational Costs:
  Content Creation & Marketing
  Ongoing Maintenance & Updates
  Staff Training & Support
Total Estimated Cost:
Initial Development & Setup Costs: $36,000 - $81,000
Ongoing Monthly Costs: $2,000 - $5,000
Total Yearly Operational Cost: $26,000 - $66,000

## Slide 19: Project Sign-Off
Project Title : Tour Booking Management System Project ID : Alpha-1xB.1257 Date : 31 October 2024 Project Manager : Wen Liang Client/Stakeholder : Arnold Aristotle Tayag
Deliverables Checklist
The following project deliverables have been completed, reviewed, and approved:
  Requirement Specification, System Design Document, Database Design, Application Development
  System Testing, User Acceptance Testing (UAT), Training & Documentation, Go–Live/Deployment
Acceptance Criteria
All project requirements, deliverables, and acceptance criteria have been reviewed and meet the standards agreed upon in the original project plan, including:
  Functional and non-functional requirements
  Performance and scalability requirements
  Security and compliance requirements
  Usability and user interface requirements

## Slide 20: Project Sign-Off
Sign-Off
By affixing your signature below, both parties agree that the project meets all user specifications and requirements and is considered officially complete. Any addendum, modifications, enhancements, or new functionalities added will be treated as new requirements and will be the subject of a new project proposal
  Project Manager: Wen Liang ___________________________
  Client/Stakeholder: Arnold Aristotle Tayag ___________________________
  Technical Lead: Hengpan Han ___________________________
  Date: 31 October 2024

## Slide 21: Reflection
Key Takeaways:
This system development project has allowed the team to put in practice key elements that are essential for project success:
  Clear and thorough requirements gathering
  Importance of stakeholder engagement & customer-centric focus
  Realistic planning and scheduling
  Early and frequent delivery of value
  Quality assurance and testing
  Risk management and early issue resolution
  Efficient communication and collaborativer approach
  Adaptability to change
  Project retrospective and continuous improvement

## Slide 22: Thank You...